Utilize the Progress Meeting Agenda as a template for maintaining

consistent discussion for progress meetings.

- Progress meeting welcome

- Record: Approval of previous meeting minutes, Contract, Location, Date, Time, and the Person keeping the minutes of the meeting (Set requirements for when minutes are to be done by, and reviewed by all attendees)

- Attendees:

| Name | Company | Present | Name | Company | Present |
| --- | --- | --- | --- | --- | --- |
|  |  | X |  |  |  |

- Safety

Toolbox talk or safety moment

Contract safety concerns

Motorist safety concerns (Discuss any accidents that have occurred prior to the meeting (vehicular or worksite personnel) and what could be added or changed to prevent future accidents.  Have an open discussion on potential MOT additions that could further enhance the safety of the work zone)

Pedestrian safety concerns

Property owner safety concerns

Public information and emergency response (first responder coordination)

Emergency services

- Maintenance of Traffic and Work Zones

Traffic control and its correctness for current work process

Condition of signs, barricades, barrels, temp pavement markings, and other devices (confirm sign and barricade reports are being submitted)

ISP and/or LEO patrol hours, status, and coordination with contract conditions (consider keeping track of cumulative hours from week to week)

Upcoming changes (discuss the need for any upcoming 2-week pre-notifications to INDOT, PIO, and stakeholders (see below) for restrictions/closures)

- Schedule

Note:  Record Critical Dates (Notice to Proceed, Intermediate Completion Dates, Contract Completion Date) for original contract and revised as per the example below:

Date description		        Original Contract Date		     Revised Date

|  | 03/15/2019 | N/A |
| --- | --- | --- |

Baseline schedule review (keep at a high level, i.e., is project ahead/on/behind schedule to meet INDOT construction contract milestones; if behind, hold independent schedule meeting as needed to discuss severity, reasons, responsibility, and potential mitigation.  In addition, include subcontractor coordination in the discussion)

Critical path review (may be better served in any as needed schedule meetings)

3-week look ahead (primary schedule related topic of discussion for progress meetings; require Contractor to provide copy of updated schedule and detailed information on planned daily major activities)

(Note:  Optional discussion items: Threats to maintaining schedule, recovery strategy, and inclement weather effects on schedule)

- Utilities and Railroads

Utility status update (keep at a relatively high level; hold independent utility meetings as needed)

Utility relocation coordination issues

Railroad and flagger coordination and submittal status update

High priority utility or railroad conflicts

- Contract Progress

Partnering and conflict resolution.  Decision tree and time frames for those decisions (Refer back to pre-construction meeting minutes where team goals have been established; continue to foster trust and open communication; commit to resolving issues promptly; and commit to talking through issues before issuing letters.  Open communication includes notifying all effected parties, including subcontractors and subconsultants)

Submittals summary:

Payrolls

Erosion control inspections (Ensure the SWQCP is up to date.  If not, this could serve as a reminder to update frequently as BMP's are added)

Other (longer lead time materials testing (e.g., SIPs, threaded tie bars, high strength bolts/nuts/washers, trial batches, etc.), and QC plans)

RFI/Shop Drawings submittal status and updates:

Review and discussion of RFI log (For submittals/RFI's that have not been resolved, discuss time frame from the responsible party on when it will be resolved/approved)

Identify action items and current responsible person/department for advancing RFI to resolution

Shop Drawings (include log with review and release/approval status)

Stormwater BMP implementation and NOT preparation

EEO issues/concerns since last meeting.

- Quantity and Estimate Payments

Quantity estimates for the pay period

Status of disputes over previous quantity estimates

Expectations for look-ahead schedule quantity estimates (add date for when next pay estimate is anticipated to be generated)

Budget “to-date” discussion (update on PO amount(s))

LD and QA status and accrual

- Change Orders

Status of change orders

Outstanding change orders (determine why outstanding; assign responsibilities for advancement to full approval)

Responsible person for action and timeline

Review change order log

- Quality/Materials and Testing

Status of failed material, appeals

Material record and certification submittals

Quality Control/Quality Assurance items for discussion

- General/Old Business Topics

Review previous action items outside the below specific topics (specifically review progress made on action items from last meeting to better develop strong accountability for resolving action items timely)

Hot topics that may need further attention outside of the progress meeting (includes risk register topics)

Locals/Public/Stakeholder concerns

Contractor concerns

Department concerns

Next Progress Meeting date/time

List of documents to be provided before the next meeting.