Rev 1/28/26

Pre-Construction Conference

Contract:

Contract Description:

Date and Time:

Location:

| # Item No. | # Topic |
| --- | --- |
| 1 - Welcome |  |
| 1.1 | Contract - Location - Project Description (Describe any Bundled projects here) |
| 1.2 | Contract Awarded to (Contractor) - Contract Amount |
| 1.3 | Contract Dates - Letting Date: - Notice to Proceed: - Road Closure/Restriction Time (if applicable): - Intermediate Completion Date (if applicable): - Calendar Completion Date: |
| 2 – Introductions/Sign In Sheet |  |
| 2.1 | - Introductions of meeting attendees – Name, Company, Job Title - Sign in Sheet – Name, Company, Email, Phone |
| 2.2 | Contract Introduction - INDOT Project Manager: - PM will do general project overview related to things like reason behind the project occurring, any issues that arose during the design phase, property owner concerns, etc. |
| 3 - Utilities |  |
| 3.1 | General Utility Information - Remind everyone that relocation plans should be on the letting website - Ascertain schedule and needed progress meetings if they haven’t already relocated - Request as-built plans for any utility that has relocated - If there are utilities that have not relocated that might cause a problem with the Contractor’s schedule, discuss setting up another meeting ASAP to formulate a contingency plan - Obtain contact information for chain of command and for emergency situations - Utilities are required to follow Buy America Certifications on all Federal Aid contracts, which should be submitted to the utility coordinator (PM should know the name of utility coordinator) |
| 3.2 | Utility Locates - Reminder to contractor to get locates prior to digging or placing construction signs - INDOT signals – contact INDOT District Traffic for locates - INDOT ITS buried facilities – Contractor is required to use the Public Access Buried Facilities App located here: https://entapps.indot.in.gov/dig/Users/Account/Login?returnUrl=/dig/ |
| 3.3 | UTILITIES – describe primary utilities listed in the CIB and relocation dates |
| 4 - Railroad |  |
| 4.1 | Railroad section required if there is a provision in the CIB - Review all railroad requirements that must be met prior to performing work within their right of way (from CIB) - Review requirements that must be met during the performance of the work within the railroad right of way (staging of material and equipment, crossings, or right of entry) - Evidence of Insurance – Contractor must follow routing as shown in the CIB. Do not just send everything to INDOT. - Note to AE – mention the mailing addresses or email addresses to which the insurance information must be sent - Discuss turnaround time for submittals - If railroad representative is present, make sure to address their specific needs/requirements |
| 5 –Contract Compliance Officer, CCO |  |
| 5.1 | General Requirements - Certified Payrolls required to be submitted electronically thru ITAP - Subcontractors, Suppliers, and Leases must be submitted via SiteXchange and approved prior to work - All subcontracts shall contain the proper documentation (FHWA-1273, wage decision, etc.). - Prime contractor should review all subcontractor documentation before submitting it to INDOT for compliance. If there are wage problems and we need corrections, must supply cancelled checks (back & front) and a payroll that matches the corrections - Lease agreement practices – submit all lease agreements to district CCO prior to execution for approval. If lease agreements are executed without approval from INDOT, we will not pay - Cannot lease laborers - Subcontractors should communicate thru prime contractor - All contractors (especially DBEs) should provide a minimum of 24 hour notice to INDOT before work occurs - Bulletin board policies - Obtain wage information from the District CCO. - Place first two pages of any permits on the board, in accordance with the Standard Specifications. - Place letter appointing your CCO officer and CCO policies on the board - Place subcontractor’s CCO officer and CCO policy on their letterhead on the board - DBE Change in Utilization Form Policy |

| 5.2 | Contract Goals - DBE % - - Minority % - - Women % - |
| --- | --- |
| 5.3 | Miscellaneous CCO Questions - Potential number of subs? - Potential start date? - Contractor CCO officer? - Contractor safety officer? - Contractor SiteXchange contact? |
| 6 - Safety |  |
| 6.1 | PPE/General Safety - INDOT personnel & consultants inspectors are required to wear appropriate PPE (class 3 vest, hardhat, steel toed boots) - All contractor personnel required to meet all OSHA requirements and per MUTCD, all personnel are required to wear a minimum of a class 2 safety vest while within the work zone - All vehicles and equipment must have appropriate warning lights to be on the job - Objects should not be left on shoulder overnight unless they are demarcated by a light or something reflective like a barrel - Equipment and materials shall not be placed or parked within the clear zone |
| 6.2 | Accidents/Safety Incidents - Accidents within the jobsite limits should be documented fully in the SiteManager diary AND contractor work zone traffic supervisor’s daily - noting locations of signs, barricades, message signs, weather conditions, etc. – recommend taking photographs - Inform accident investigation to AE, District Safety, and contractor’s safety officer immediately |
| 6.3 | INDOT Safety Briefing - Required to be filled out daily and kept in the file – should include all consultant inspection staff |
| 6.4 | ISP & LEO Hours - Coordination will occur through INDOT PEMS - If used, PEMS will add hours worked in daily diary - Determine LEO hours included in contract - Determine ISP hours allowed for in contract |
| 6.5 | Emergency Contacts - Contractor required to provide at least 2 contacts, available 24/7 for the prime contractor and 1 contact for the sign and barricade company - Contractor shall place on the bulletin board - INDOT shall place on the wall within the field office - INDOT shall place contact information in CARS and provide to appropriate people - Who will be in charge of the day to day operations for the Contractor? |
| 6.6 | Emergency Services - Closures, restrictions, and re-routing of traffic requires communication to all emergency services |
| 6.7 | Safety concerns/comments? |

| 7 – Traffic & Traffic Control |  |
| --- | --- |
| 7.1 | Signals - Do timing of any signals need to be adjusted during construction? Phasing changes needed? - Will construction affect roadway or interchange lighting? - What can be done with respect to phasing that will eliminate or reduce the possibility of creating an unsafe situation due to lack of lighting? - PEMS should contact district traffic prior to construction in order to address their needs. |
| 7.2 | Traffic Control Supervisor and Reports - Contractor to provide Work Zone Traffic Supervisor certifications to the PEMS for prime, sign sub, and any other person performing lane restrictions - Weekly sign and barricade reports are required on all contracts - This report shall include when a temporary traffic control device has been installed, removed, relocated, repaired - All traffic control devices shall be inspected daily - Certified Worksite Traffic Supervisor shall complete or review the report before submittal – requires signature of the person who completed the report and shall be initialed by the CWTS - The Traffic Control Device Report shall be submitted weekly - PEMS will sign and date the report when received, however they are not responsible for the report’s completeness and accuracy - All repairs to deficiencies must be repaired within 24 hours - PEMS to perform periodic checks of traffic control devices, including night check |
| 7.3 | Maintenance during Construction - Work shall be maintained until the contract is accepted - Once construction operations begin, Contractor to repair areas as needed within project limits |
| 7.4 | Unofficial Detour/Local Haul Routes - Is there an unofficial detour? If so, what is it? Does it need to be recorded? - Local haul route requirements? Discuss repairs and responsibilities |
| 7.5 | Access Concerns - Contractor required to maintain pedestrian, driveway, and mailbox access at all times |
| 8 – Public Information/Customer Service |  |
| 8.1 | Public Relations Director - Insert Contact Information – District External Communications/PIO - PEMS will reach out to District Communications 2 weeks prior to MOT changes, including all phase changes, restrictions, closures |
| 8.2 | Customer Service - For customer inquiries – all should be referred to the INDOT phone number 1-855-INDOT-4-U or website: www.indot4u.com |
| 9 – Environmental/Stormwater Management |  |
| 9.1 9.1 Cont’d | Stormwater Management - For contracts requiring a Construction Stormwater Permit (CSGP), a Stormwater Quality Control Plan (SWQCP) shall be developed and submitted to the PEMS - Shall be submitted a minimum of 14 calendar days prior to beginning land-disturbing activities - A pre-disturbance meeting shall be held on contracts requiring a SWQCP - Anticipated date of meeting? - If requested in writing, the pre-disturbance meeting requirements may be waived in part or in full with the approval of the PEMS - Waterways Stormwater Quality Manager (SWQM) – required on contracts requiring waterway permits and not requiring a CSGP – the individual shall have successfully completed the Department’s Construction Stormwater Training course and hold a current certificate - CSGP SWQM – required for contracts with a Construction Stormwater General Permit (CSGP) – the individual shall have successfully completed the Department’s Construction Stormwater Training course and hold a current certificate as a CESSWI, or a CISEC, or a CEPESC, or the EPA Construction Inspection Training Course, or an approved equivalent - IC 203 borrow/waste site form shall be submitted a minimum of 14 days prior to the start of operations for all borrow and disposal materials, including millings |
| 9.2 | Contracts without the Stormwater Management Budget and those only requiring waterway permits - Contractor shall submit a written site plan at least seven calendar days prior to the start of construction - Plan shall describe: the contract site; locations of all equipment storage areas, staging areas, fueling locations, construction trailers, batch plants, and concrete truck washout locations; and a material handling and spill prevention plan for sanitation facilities, fueling, and concrete washout locations. |
| 9.3 | Erosion and Sediment Control (ESC) Inspections - On contracts requiring a CSGP, inspections on all work areas associated with the permit shall be inspected - Inspections shall be submitted at a minimum of once per calendar week, 24 hours prior to a qualifying rain event (1/2 inch), or by the end of the next day following the event - A single inspection performed after a rain event shall satisfy the requirement for both the rain event and weekly inspection - No more than three inspections shall be required in a calendar week - Inspections shall be submitted electronically using the current version of the Department’s stormwater inspection application - A paper inspection form shall only be used if directed by the PEMS or if the application is out of service - All BMP deficiencies are required to be corrected within 48 hours. Immediate deficiencies are required to be corrected within 24 hours (includes weekends and holidays). Refer to 205 spec for info on BMP vs. immediate deficiencies. - Identify INDOT District Erosion Control Specialist |
| 9.4 | Permits (determine if the following permits are in effect on the contract) - Army Corps of Engineers 404 – Type? - Army Corps of Engineers 404 – Regional General? - IDEM 401 Water Quality Certification? - DNR Construction in a Floodway? - Construction Stormwater General Permit? - Other? |

| 9.5 | Commitments - Review commitments provided |
| --- | --- |
| 10 – Testing/Materials |  |
| 10.1 | Contractor Requirements - Build America, Buy America Requirements in special provisions - Build America, Buy America certifications required on all materials outlined in the special provisions – must be signed by the Prime Contractor - Asphalt and concrete mix designs submitted and approved prior to use - Will e-ticketing be utilized by the contractor? - If so, discuss what & how to get set up - E-ticketing incentive – see memo 23-08 for eligibility and implementation - Provide material certifications prior to incorporating into work - Provide material source list to the PEMS - Submit QC plans in accordance with the CIB, specifications, GIFE, ITM 803 - Review USPs for special testing procedures - Discuss continuous deck pour feasibility on bridge contracts |
| 10.2 | INDOT Requirements - Materials - Certify that all testing personnel have up to date testing credentials, or obtain appropriate certifications - PEMS to provide the testing credentials to District Testing Engineer and AE for all inspection staff prior to the start of construction - Directive 109 will be required to be completed to satisfy material record at the end of the contract |
| 10.3 | Bridge Beams - Contractor to provide to the PEMS the name of prestressed concrete or steel beam fabricator, plant location, point of contact, estimated month/year fabrication will begin and duration of fabrication - PEMS to email to structuralmemberqainspection@indot.in.gov |
| 11 – Contractor Submittals |  |
| 11.1 | Schedule - Work may not start until schedule has been submitted - Planned start date? - Planned work hours? - Block out dates? - Work hour/lane restrictions time frames? - Schedule should account for turnaround time for submittals, and all requirements set forth within the permits - Contractor shall update schedule when required per the Specifications and as directed by the PEMS |
| 11.2 | Coordination with Adjacent Projects - List Adjacent Projects & Prime Contractors |

| 11.3 | Required Submittals not already discussed - Signature Affidavit - Pile Hammer(s) (if applicable) - Cofferdam/Causeway (if applicable) - Category 1 & 2 temporary traffic device report - Shop drawings/working drawings as outlined in the CIB and specifications - List of subcontractor point of contact (Name and email address) |
| --- | --- |
| 12 – Surveying/Construction Engineering |  |
| 12.1 | Miscellaneous - Coordinate with County Surveyor prior to setting section corners or applicable monuments - Stationing and construction limit staking must be in place before work begins - R/W staking must be done by licensed surveyor |
| 13 – Change Orders/Contract Authority |  |
| 13.1 | Identify and List the Chain of Authority - INDOT PEMS - INDOT Construction Support/Section Engineer - INDOT Area Engineer - INDOT District Construction Director - Contractor superintendent? - Contractor project manager? - Contractor area manager/president? |
| 13.2 | Partnering & Problem Resolution - Partnering video 1 – Why Win-Win Negotiations are Good for Business - https://www.youtube.com/watch?v=Y4hFpppPsWQ - Partnering video 2 – How Miscommunication Happens (and how to avoid it) - https://www.ted.com/talks/katherine_hampsten_how_miscommunication_happens_and_how_to_avoid_it - If official partnering is on the contract – resolution time frame will be established at that time - If not included, times suggested PEMS – 1 day, AE/Contractor PM – 3 days, DCD/Area Manager or President – 5 days |
| 13.3 | Change Orders/Time Extensions/Claims - Timely submittals expected from the Contractor and timely review expected from INDOT - Contractor required to utilize the Change Order Request Form available on the INDOT website - Change order pricing will be reviewed in accordance with standard INDOT procedures - Funding – PEMS to keep track of funding balances and request additional funds as necessary utilizing the Cost Change Request Form – must be justified by approved change order - If the Contractor requests a contract adjustment for a changed condition in accordance with 104.02, notification shall be made in writing before work is begun and expenses relating to the request are incurred in accordance with 105.16. - PEMS to notify the AE and PM immediately upon discovery of the need for a change order - Who signs change orders/time extensions for Contractor? |

| 13.4 | Weekly Reports - IC 124 – Weekly Report of Controlling Operation will be sent to the Contractor - Contractor has 7 days to review and comment per the specifications - Who signs weekly reports for the Contractor? |
| --- | --- |
| 14 – Contractor Payment |  |
| 14.1 | Pay Estimates - Two estimates per month during ongoing work operations - Who will sign estimates on behalf of the Contractor? |
| 14.2 | Payment Holding - Payment of estimates can be held for CCO violations, ESC violations, traffic control violations, out of date schedules, not providing material certifications in a timely manner, late payrolls, etc. |
| 14.3 | Payment Quantities - When possible, agree to quantities with the Contractor daily - Contractor to provide all tickets to justify payment |
| 15 – Field Office/Progress Meetings |  |
| 15.1 | Field Office - Required? - Has one been located by the Contractor yet? - Anticipated move in time frame? |
| 15.2 | Progress Meetings - Will be held at agreed upon interval as work is scheduled - Meeting agenda has been standardized – REQUIRED for all contracts to use - Refer to memo 23-09 for locations of the form to be used |
| 16 – Final Closeout |  |
| 16.1 | Final Closeout - IC 675 – Agreement to use Plan Quantities as Final Payment – this agreement must occur at the start of the contract and obtain approval from the area engineer at the start of the contract. If this is not completed at the start of the project, the item will not be eligible to be reported utilizing that form upon submittal of the Final Construction Record - Once all contract work is complete, PEMS to notify AE that the project is ready for a Pre-Final Inspection - Stress early submittal of all material record information to help speed up the FCR process - INDOT required to enter key dates and milestones in SiteManager or Informational Dates in AWP as they occur - All contracts will utilize the electronic FCR & intelligent file cabinet. - This means all contract documents including weight tickets shall be uploaded into ProjectWise. - The Final Review Officer will send the final IC 642 to the Contractor for review, - Contractor then has 30 days for review, questions, signature, and return |
| 17 – Contract Documents |  |
| 17.1 | Unique Special Provisions & Pay Items - List and review |
| 17.2 | Pre-letting Revisions - List and review |

| 17.3 | Construction Changes - Per memo 13-12, the Contractor should designate a person whom construction change notification will be sent to – PE to send Contractor/PE/AE information to Scott Teal - List and Review |
| --- | --- |
| 17.4 | Contractor Questions and Answers - List and review |
| 17.5 | Contractor Performance Evaluations: Discussion on performance expectations and snap shots. Comments provided for ratings above or below “0”. |
| 18 – Meeting Wrap Up |  |
| 18.2 | Question/Comments from any attendees? |
| 18.3 | PEMS to complete meeting minutes within three business days, send to AE for review, then after approval by the AE, disburse to ALL meeting invitees (not just the attendees). Please reply all to the meeting invite and attach the meeting minutes in PDF format. |